## Sheet1
Sr. No. | Module/Task | Assignee | Start Date | End Date | Status
1 | Source Reports | Shree Harshini | 2016-11-14 | 2016-11-18 | started
2 | Search by ISSN | Kirti | 2016-11-15 | 2016-11-17 | working on
3 | Dynamic Reports | Aditya | 2016-11-21 | 2016-11-25 | working on
4 | Counter/Custom | Kirti | 2016-11-18 | 2016-11-22 | started
5 | Selected platform | Shree Harshini | 2016-11-21 | 2016-11-23 | working on
6 | Acess Details | Shree Harshini | 2016-11-24 | 2016-11-25 | finished
7 | Libray Account | Kirti | 2016-11-14 | 2016-11-14 | finished
8 | Integration Partners | Kirti | 2016-11-23 | 2016-11-25 | working on
9 | Additional User | Aditya | 2016-11-16 | 2016-11-18 | working on
10 | Upload data | Kirti | 2016-12-01 | 2016-12-02 | finished
11 | Export data | Kirti | 2016-11-28 | 2016-11-30 | finished
12 | Contact Us | Aditya | 2016-11-14 | 2016-11-14 | finished
13 | FAQ | Shree Harshini |  |  | Finished
14 | About Us | Shree Harshini |  |  | Finished
15 | Dashboard + graphs | Shree Harshini | 2016-11-28 | 2016-12-01 | working on
16 | Home | Aditya | 2016-11-15 | 2016-11-15 | Finished